Global Action Days – My Actions Matter!

Timeline

| 9 March | Online Meeting for National Operators (NOs) - Briefing by FEE & Now.Here. |
| --- | --- |
| 10 March | NOs start creating a list of target schools that they intend to recruit and check that they have a valid contact email address. General info about the campaign to share with schools can be found here: https://www.ecoschools.global/my-actions-matter |
| 22 March | FEE will send out a PR package with a template email for schools, a poster about the campaign, social media posts, hashtags, etc. |
| 22 March and onward | NOs to promote the campaign on a national level and recruit schools. |
| Late March | FEE will send supporting documents with action descriptions (for offline implementation and translation) to NOs. |
| 7 April | Open webinar for schools – Introduction to campaign and to create enthusiasm and encourage enrollment . |
| 7 April | Now.Here. will send links and activation codes to FEE. |
| 8 April | FEE will send links and activation code to NOs, who will start sharing this with their schools. Participants can download and explore the TreasureEarth app, but will not see the GAD campaign in the app until the 19th. |
| 19 April | Campaign contents will become visible and participants may begin their journey. |
| 22 April (Earth Day) | Official start of the campaign |
| 26 April | Last date for registration. Users who sign up after this date will not be able to complete all 21 days. |

Frequently Asked Questions

- How much do the schools have to pay to participate?  
$zero - it is free.

- What languages will the campaign be available in? 
English, but action descriptions will be available in Word format for NOs to translate.

- What if participants don’t have a mobile phone?  
Content will also be available offline as a Word document.

- Who will provide first level support and explanations? 
FEE

- Who created the content of the campaign? 
FEE & Now.Here. co-created the content.

- How secure is the personal data?  
Compliance to GDPR. AWS and physical servers in Singapore, Data Policy, etc.

Downloads will be through the actual app stores, and therefore secure.

- Is this initiative aligned with the strategic goals of FEE for the next few years? 
Yes

- Will individual communities be able to see their achievements?  
Yes

- How long does each action take to complete?  
2-20 minutes

- Are they all individual actions, or will there be any “collective” actions? 
One collective action per sprint/theme – so 3 in total.

- Will participants be able to continue using the app after the campaign? 
Yes

- Can we invite parents and family members? 
Yes, however we wish to focus mainly on the school community.

- What if a participate starts “late” after 22nd April?  
They can start as late as 26th April and will have 21 days. If participants start later than this date, they will not be able to complete the whole campaign.

The content is revealed day after day.  “Day 1” will be revealed when you start.  Day 2 on second day.

- What if I/we discover a bug in the app? 
You can fill up a bug reporting form that will be provided.